Terms of Reference

Services for Proofreading, Layout and Design of ASEAN Disaster Resilience Outlook

Background of Assignment:

The ASEAN Secretariat and Singapore Civil Defence Force are developing a publication tentatively titled “ASEAN Disaster Resilience Outlook (2021)- ASEAN’s Journey for a Disaster-Resilient Region” (ADRO). The ADRO publication will be submitted to the ASEAN Committee on Disaster Management (ACDM) by 24 September 2021 for endorsement. The final design of ADRO shall be made available by 20 September 2021 prior to the submission to the ACDM. The launch of the publication will be conducted at the sidelines of the 1st AMMDM Meeting Plus China to be held in the week of 11-15 October 2021.

The ASEAN Secretariat is seeking a contractor to provide services for proofreading, layout and design for the ADRO publication, including also to create visually interesting graphs and charts. The contractor is required to carry the activity of the overall designing and layouting of the publication which potentially consists of around 100 A4 pages. The layout design and specifications will be decided in consultation with the Disaster Management and Humanitarian Assistance (DMHA) of the ASEAN Secretariat. This will include graphs/charts, format/style, typesetting, styling, colour, placement of photos, logo, etc.

Where deemed necessary and where the ASEAN Secretariat does not provide the contractor with cover and inner-page visuals, the contractor will be responsible for providing these visuals and presenting them to the ASEAN Secretariat. The designs shall be entirely in line with ASEAN Corporate Design Manual

(https://www.asean.org/storage/images/2015/May/asean_resource_kit/ASEAN%20Corporate%20Design%20Manual%202015.pdf)

Expected Deliverables:

“Ready to Print” and “Ready for Online Sharing” design and layout for the ADRO.

Duration of Assignment:

The contractor is expected to work from 1 August to 30 September 2021 with possible extension (subject to the request and approval from the DMHA Division)

Reporting:

The contractor will work closely with and report to the Head of DMHA Division of the ASEAN Secretariat.

Required Competencies:

- Proven 3-5 years’ experience in graphic and layout designing / publication production;

- Excellent command of Adobe applications including Photoshop, illustrator and InDesign;

- Advance understanding of vector-based imagery, such as maps, logos and infographic;

- Proven ability to deliver high quality results under tight deadlines;

- Proven ability to coordinate, follow instructions and work under pressure either part of team or individually.

Requirement

The contractor should submit a quotation in Indonesian Rupiah (IDR).

****