TERMS OF REFERENCE (TOR)

Consultancy for the Operation of ASEAN Gallery 2022

- Background

Established in 2001, the ASEAN Gallery is a dedicated art space at the ASEAN Secretariat (ASEC) housing artworks from the ten ASEAN Member States, ASEAN’s external partners, and private donors. The Gallery, which is being operated on a non-profit basis, is managed by the Community Relations Division (CRD) to reach out to ASEAN’s stakeholders through the art medium.

With a view to further promoting appreciation for ASEAN arts among the public, since 2016, CRD has taken concrete steps to improve the operations and management of the Gallery. The improvement covers data administration, maintenance of ASEC artwork collection as well as outreach art event establishment.

In 2018, a consultant was hired to provide technical support to the administration of ASEAN Gallery.  Since then, the consultancy was undertaken annualy for a period of one full year.  However, for 2022, the consultancy will be offered in the 2nd semester from August to December (five months).

- Objectives

The aims of this project are:

- To assist CRD in developing a robust management system for the Gallery.

- To provide ASEC with guidance on proper maintenance of the Gallery and its collection

- To help strengthen CRD’s outreach program using the Gallery as a platform.

- Scope of Work

For this project, the Consultant is expected to deliver the following activities/outputs:

- provide valuation of selected art works in the gallery (see attachment);

- provide professional and expert advice on, wherever appropriate, the following:

  - enhancing the management of Gallery and preservation of its collection;

  - identifying suitable artworks among existing stock/inventory of ASEAN Gallery collection that may be displayed in ASEAN Secretariat building’s public spaces for aesthetic and public outreach purposes;

  - selected ASEC-driven art-related activities/ programme e.g. ASEAN Artists Residency Programme (AARP).

- conduct one themed ASEAN Gallery exhibition (including planning, organising, and post-event follow up);and

- submit final report of services and outputs provided.

- Expected Tasks, Timelines, and Deliverables

| Timelines | Expected Tasks & Deliverables |
| --- | --- |
| 1 August – 31 December 2022 | the Scope of work, Point III; a, b & d. |
| 1 August – 31 December 2022 | the Scope of work, Point III; c. |

- Administration, Reporting and Coordination

A lump sum amount will be paid to the Consultant covering his/her professional fee and one themed exhibition at ASEAN Gallery. The Consultant is expected to conduct work from home/ own office and arrange initial meetings with ASEC as needed.  If and when necessary, ASEC will arrange for the Consultant to visit ASEAN Secretariat for specific tasks.  Unless stipulated otherwise, flights, accommodation, daily subsistence allowance, airport transfers and the production of exhibition as outlined in 3 – “Scope of Work.” Point C, will be under the responsibility of the consultant.

- Requirement for the Submission

The prospective bidder is required to submit the following:

- Technical

- having at least 5 years of experience in Gallery consultancy/ art projects management, especially on Southeast Asian art and culture (please provide evidence);

- submitting the following:

- Cover letter addressed to Community Relations Division, ASEAN Secretariat, sharing his/her interest to work on this consultancy with clear reason;

- A proposal indicating how they plan to fulfill the TOR of the project (point a to point d). The proposal shall include overall approach, methodology, work plan, timeline and contigency plan (in case the work plan does not meet timeline).

- Up-to-date curriculum vitae

- Brief description of similar consultancies completed or currently being carried out (Please provide necessary evidence).

- Financial

A detailed financial proposal indicating the costs (IDR for local bidders and USD for international bidders) required for undertaking the assignment.

- TERMS OF PAYMENT

50 % upon signing of Purchase Order

20 % upon CRD’s confirmation of completion of deliverables a, b and d listed in “3. Scope of Work”;

30 % upon CRD’s confirmation of completion of deliverables c listed in “3. Scope of Work”