## Spec Form-For Invitations
For Invitations
SPECIFICATION FORM
Quotation for Fuel Tank Construction
Closing date for Quotation Submission: [Procurement to fill in]
No. | Items Description |  | Qty | UoM | Unit Price (IDR) | Total Price (IDR)
1 | The scope of work installation fuel tank capacity 10,000 liter consist of but not limited to:
| a. Supply and install new fuel tank capacity 10,000 liter material mildsteel SS400. All of tank surface (inside and outside) must be coated with anti-rust material and painted anti-rust. C/W : Manhole, foot, ladder, inlet, outlet, Drain, Ventilation, Level sight control (refers to drawing). The cost include mobilization and on-site placement determined by ASEC. |  | 1 | unit |  | 0
| b. Installation roof to protect the fuel tank, include frames (CNP zincalum light steel and spandeck roof sheet) include all accessories |  | 20 | m2 |  | 0
| c. Excavation of foundation |  | 3.5 | m3 |  | 0
| d. Install rock masonry foundation |  | 3.5 | m3 |  | 0
| e. Reinforcement beam, lintel beam, colomn |  | 1.3 | m3 |  | 0
| f. Install brickwall |  | 27.6 | m2 |  | 0
| g. Plastered brick wall |  | 55.2 | m2 |  | 0
| h. Painted wall |  | 55.2 | m2 |  | 0
| i. Compacted sand to be filled in the fuel tank chamber |  | 7 | m3 |  | 0
2 | Purchase diesel fuel , ex Pertamina Dex CN 53 |  | 3000 | liters |  | 0
Total | [5 empty] | 0
Delivery date |  | : After PO
Availability of stock |  | : Ready stock
Warranty (required/optional/not required) |  | : required, 6 months
Terms of payment |  | : DP 20%, 80% After completion of works
Validity of Quotation |  | : 30 days of the Quotation Date
General guideliens /Ketentuan:
1 | Please put your signature below or company's stamp
Mohon disertai tanda tangan PIC atau cap perusahaan;
2 | Please state the availability of stocks for the above items/
Mohon cantumkan ketersediaan stock barang-barang diatas;
3 | All items provided shall be genuine. Shall the above items provided are not genuine, we will cancel
the purchase of the above items/
Semua barang yang disediakan wajib barang asli. Apabila setelah pengiriman barang-barang di atas ditemukan tidak asli,
maka kami akan membatalkan Purchase Order yang sudah diterbitkan.
4 | The price in this quotation shall be valid for 30 (thirty) days commencing on the date of submission of quotation
Harga satuan yang tertera pada penawaran wajib berlaku selama 30 (tiga puluh) hari terhitung sejak tanggal penawaran;
5 | Please exclude VAT 10%, as ASEAN Secretariat is NOT subjected to VAT/
Mohon tidak mencantumkan PPn 10% pada harga penawaran karena Sekretariat ASEAN tidak dikenakan PPn;
[Signature or Company's Stamp]
[Vendor to fill in]
…………………………………..
Contact Person:
Company:
Date/Tanggal: