Terms of Reference

Event Organiser for the Event “ASEAN-Japan friendship and cooperation 50th Anniversary Symposium” Promoting Resilient and Sustainable Agriculture and Food System through Innovation: ASEAN's Initiatives and Japan's Contribution

- Introduction

- In most ASEAN countries, the food and agriculture sector remain as a strategic sector in providing a major source of employment opportunity and income for a large population of the region. More importantly, it contributes to ensuring national and regional food security and nutrition in ASEAN. However, globally and regionally, agriculture is facing various existing and occurrent challenges such as constantly growing food demand due to steady population growth, worsening climate change, devastating effect of the Covid-19 pandemic, intensifying political tensions and so forth.

- For ASEAN region, considering the needs to transform agriculture in the region to more sustainable, ‘Regional Guidelines for Sustainable Agriculture in ASEAN’ was discussed among ASEAN Member States (AMS) and endorsed at the 44th meeting of ASEAN Ministers on Agriculture and Forestry (AMAF) on 25th October 2022. In this meeting, Japan‘s Proposal for Strengthening Cooperation with ASEAN towards Enhancing Resilient and Sustainable Agriculture and Food Systems for Ensuring Regional Food Security (Midori Cooperation Plan) through innovation etc. was welcomed by AMS.

- The direction of these policies and strategies of ASEAN and Japan indicates that the both parties clearly recognize the importance of resilient and sustainable agriculture and food systems. Based on these similarities, a symposium that expected to be attended by policy makers, businesses, entrepreneurs, researchers, and academia, aims to mutually share the recent policy initiatives, knowledge and technologies on building resilient and sustainable agriculture food systems towards securing food security in the region.

- For successful conduct of the event, a Jakarta-based professional Event-Organizer (EO) will be hired to run the event.

- Objective

- The Symposium event aims to:

- Promote better understanding of policy makers on effective policies, regulations and initiatives for enhancing resilient and sustainable agriculture and food system,

- Explore transferable and applicable innovative technologies and practice among participants,

- Catalysis the partnerships needed for transformation of agriculture and food system into more resilient and sustainable,

- Share key messages from the ASEAN Leaders’ Declaration on Strengthening Food Security,

- Deepen understanding of ‘MIDORI Cooperation Plan’ and gathering inputs and suggestion for further its improvement, and

- Contribute to ensuring regional food security through achieving the above objectives.

The selected EO will assist user to ensure that the objectives above are met.

- Scope of Work

- The selected EO will be responsible in managing the event. Specific details of responsibility are as follows:

- To provide a concept document, a compelling grand for high-level event that will be implement during the activity. The EO shall execute the concept from the beginning until the end as user approve.

- To develop poster of the event (in consultation with the ASEAN Secretariat, MAFF CBF PMT, ERIA, and Mission of Japan to ASEAN). Several parties will circulate via its respective social media.

- To provide logistical arrangement for the symposium event, which include, among others

- Registration of the participants (include the guest book)

Note: The invitation will be done by the ASEC. The EO will manage the registration of the participants.

- Arrangement of the stage (including design for virtual background), seats, screens design for presentation, decoration for stage, generator, sound equipment, microphone, multimedia projector, video equipment, sound system, screen (LED), and other equipment

- Arrangement of seating and decorations on the center of delegation seat

- Arrangement of all necessary and additional equipment tools for proceeding hybrid event including all installation and technical requirements

- 1 PIC for request assistance or urgent coordination (also responsible for formulating the Symposium Report result)

- 2 manpower for the registration desk

- Documentation (video documentation, photos documentation)

- 11 Ushers/Liaison Officer for each AMS + Timor Leste

- 1 Master of Ceremony

- 1 Time Keeper

- 1 Program Director

- Interpreter from English-Japanese (include interpreter soundproof booth)

- 1 PIC for all equipment and technical installation

- 150 set of interpreter device

- Recording of the event from the beginning until the very end (recorded through in person).

- Layout of food and beverages arrangement

- Setting Poster at Foyer

- Setting booth for exhibition at Foyer

- Lanyard for the delegates

- Other logistics issues necessary for the successful conduct of the event (please refer to attached Appendix 1 for detail of manpower and technical requirement)

- To provide platform where participants can provide their comments/feedback of the event.

(Note: ASEC will do the analysis of the submitted responses)

- Expected Tasks, Timelines, and Deliverables

- The expected deliverables output of EO are as follows:

| Milestones | Deliverables | Timeline |
| --- | --- | --- |
| 1 | Confirmation of the design (virtual background, lanyard, and e-flyer) | First week of November |
| 2 | Finalisation of the Program Script | First week November |
| 3 | Name list of 11 Liaison Officer | Second week of November |
| 4 | Submission of Recorded video and Summary Report | TBC |
| 5 | Submission of the Participants’ feedback | TBC |
| 6 | Submission of invoices | TBC |

- Administration, Reporting and Coordination

- The ToR for this assignment will be issued by ASEC. The EO shall report directly (include the report on Symposium results) to the MAFF CBF PMT.

- Requirement for Submission

Technical

- Interested Event Organizer candidates are invited to submit a proposed package in English. Candidates will be given plus points if they can provide more information necessary to support successful conduct of the event.

- Provide sample of past work on similar events. Candidates will be given plus points if they had work experience with ASEAN Secretariat.

- Availability to respond to urgent requests for assistance and coordination by providing 1 designated manpower as PIC since being selected as a designated vendor.

- Availability to fulfil all requests for manpower requirement and technical requirement (refer to point III).

- Provide Curriculum Vitae (CV)/Portfolio in English for the Program Director manpower that highlights the following criteria:

- Experience in organising international events (Symposium or Conference or workshop or dialogue). Candidates will be given plus points if they had work experience with ASEAN Secretariat.

- Experience in managing hybrid event proceedings (Symposium or Conference or workshop or dialogue). Candidates will be given plus points if they had work experience with ASEAN Secretariat.

Financial

- A detailed financial proposal indicating the costs (IDR for local and USD for international) required for undertaking the assignment.

- The term of payment for this project will be in the following manner:

1st Payment: 30% upon completion of milestones 1, 2, and 3

Final payment: 70% upon completion of milestone 4, 5, and 6

*****