SPECIFICATIONS FORM

Title of work:                      Document Translation Service (Indonesian to Japanese)

Completion of work:	      1st batch of translation by 29 July 2024 at the latest

| ### General Works: | Provide document translation (Indonesian to Japanese) based on Model Answers (Subfolder 1 – 4) Document Type: Ms. Word, Ms. Excel Quantity: 49,955 Words |
| --- | --- |
| Technical Specifications: The document details are as follows: - Subfolder 1 contains: Food Safety Training Groupwork Sheet - Subfolder 2 contains: Audit Training Groupwork Sheet - Subfolder 3 contains: Food Safety Training and Audit Training pre-assignments, pre- and post-surveys - Subfolder 4 contains: Food Safety Training and Audit Training tests and retests Link to Model Answers: https://drive.google.com/drive/folders/1pZetbSZqGvzrAy__CDJjZc8nGVTfwA4h?usp=drive_link In addition to both Food Safety and Audit Training documents: - The materials attached are model answers in English. However, please calculate the translation cost for Indonesia-Japanese language. - Please refer to ‘1. Answers’ files on each Subfolder. Please calculate the texts in red color. The ‘2. Materials’ files are also uploaded for reference only, not for calculation. - Please calculate the cost following the below guideline: - Groupwork answer sheets (Subfolder 1&2) will be calculated for approx. 4 groups. Please multiply the translation cost for all Food Safety and Audit Groupwork Sheets by 4 to the calculation. - Answer sheets of pre-assignment, pre- and post-surveys, and tests and retests (Subfolder 3&4) are to be calculated as it is. - The materials attached are model answers. The actual materials to be translated will be shared in batches following the translation timeline. - The materials are in Ms Word and Ms Excel format. All needs to be translated and finalized into the same format accordingly. |  |
| Indicative Timeline The vendor should be able to deliver the complete result within the required delivery date following below timeline: Activity; Days; Date. Translating Food Safety Training Pre-Assignment and Pre-Survey; 6 working days; 4th week of July. Translating FSM test; 12 working days; 3rd week of August. Translating FSM retest; 6 working days; 1st week of September. Translating Audit Pre-Assignment; 6 working days; 3rd week of September. Translating Audit test; 11 working days; 3rd week of October. Translating Audit retest; 6 working days; 1st week of November. Translating Food Safety Training and Audit Training group worksheets, and post-survey; 21 working days; 3rd week of November. |
| Quotation Validity | Up to 60 days |

CONDITIONS:

- The vendor is compulsory to follow and provide all technical specifications as elaborated in the Specifications and be able to deliver the complete result within the required delivery date indicated in the Timeline.

- Please be informed that the documents to be translated are subject to change due to 1) the length of answers of each person/group and 2) the number of participants who need to take the retest for Food Safety and Audit training. Hence, the payment will follow the final cost based on the actual end result.

- Terms of payment: 100% payment upon completion and acceptance of the service

…………………………………….

(Supplier)

Date: …………………………..