## Spec Form-For Invitations
For Invitations
SPECIFICATION FORM
Repair Prayer Room at ASEC Heritage and New Building
Closing date for Quotation Submission: Refer to the invitation and web advertisement (asean.org)
No. | Items Description |  | Qty | UoM | Unit Price (IDR) | Total Price (IDR)
Repair of Prayer Room at the Mezzanine Floor ASEC Heritage Building
A. | Repair Damaged Wall caused by High Humidity
1 | Remove and dispose damaged textured finish wall until plaster layer |  | 44 | m2 | Vendor to fill | Vendor to fill
2 | Wall Plaster Work (with antiwater penetration) |  | 44 | m2 | Vendor to fill | Vendor to fill
3 | Repaint Wall (provide 2 layer: Alkali killer Paint + interior Weathermaster Paint), Color : Morning Dew Texture : Flat finish |  | 44 | m2 | Vendor to fill | Vendor to fill
B. | Repair Old Wall and Partition
1 | Repaint Wall (provide 1 layer: Interior Paint), Color : Morning Dew |  | 85 | m2 | Vendor to fill | Vendor to fill
Repair of Prayer Room at the 6th Floor North Tower ASEC New Building
1 | Supply and Install Ceramics for wall at the ablution area: - Type : Roman ceramics (refer to existing) - Dimension : 0.5mx0.25m (refer to existing) - Color refer to existing |  | 18 | m2 | Vendor to fill | Vendor to fill
Notes : 1) The vendor must provide material, supporting tools, equipment and manpower to complete the work 2) The vendor must comply with safety standards while working and maintain work without any accident or damage to ASEC property (provide safety net, personnel protective equipment, etc). If there is any damage occurs caused by the vendor work, the vendor must repair until satisfactory condition and approved by ASEC. 3) The vendor is required to ensure the working area remains tidy and clean Working Time : weekdays : 05.00pm - 10.00pm weekend or national holiday : 08.00am - 10.00pm
Total | [5 empty] | 0
Delivery date |  | : After PO, must be completed in 2024
Availability of stock |  | : Ready Stock
Warranty (required/not required) |  | : 3 month (workmanship guarantee)
Terms of payment |  | : 20% Down Payment (upon receipt of confirmed PO) 80% Final Payment (after all work has been completed)
Validity of Quotation |  | : 60 days
General guideliens/Ketentuan:
1 | Please attach this Specifications Form to your quotation with your signature below or company's stamp;
Mohon melampirkan Spec. form ini pada penawaran disertai tanda tangan PIC atau stempel perusahaan;
By signing this Specification Form, you/your company agree to fulfil with all requirements as stated above.
Dengan menandatangani Form Spesifikasi ini, Anda/perusahaan Anda setuju untuk memenuhi semua kriteria tersebut diatas.
2 | Please state the availability of stocks for the above items;
Mohon cantumkan ketersediaan stock barang-barang diatas;
3 | All items provided shall be genuine. Shall the above items provided are not genuine, we will cancel the purchase of the above items;
Semua barang yang disediakan wajib barang asli. Apabila setelah pengiriman barang-barang di atas ditemukan tidak asli,
maka kami akan membatalkan Purchase Order yang sudah diterbitkan.
4 | The price in this quotation shall be valid for 30 days commencing on the date of submission of quotation;
Harga satuan yang tertera pada penawaran wajib berlaku selama 30 hari terhitung sejak tanggal penawaran;
5 | ASEAN Secretariat is exempt from the imposition of Value Added Tax. However, vendor may use Faktur Pajak 010 to collect VAT.
ASEAN Secretariat dibebaskan dari Pajak Pertambahan Nilai (PPn). Akan tetapi, vendor dapat menggunakan Faktur Pajak 010 untuk memungut PPn.
Signature and or Company Stamp
Contact Person:
Company:
Date/Tanggal: