TERMS OF REFERENCE (“TOR”)

FOR CONSULTANTS TO CONDUCT

A Joint Study on Cooperation on New Trade Agendas

- Background

During the 21st AKFTA IC Meeting, Korea proposed conducting a Joint Study on Cooperation in New Trade Agendas, aimed at identifying potential areas for inclusion in the enhancement of the AKFTA. The Meeting endorsed the Joint Study, to be supported by the AKFTA Economic Cooperation (AKEC) Fund, which will complement the findings of the Joint Review Study. These proposed enhancements are intended to ensure that the AKFTA remains relevant to businesses, modern, forward-looking, and responsive to both regional and global developments

Since the ASEAN-Korea Free Trade Agreement (AKFTA) entered into force, the global and regional economic landscape has undergone significant transformation. The emergence of new multilateral agreements, such as the Regional Comprehensive Economic Partnership (RCEP), and the evolving trade relations of both ASEAN and Korea with external partners, have reshaped the dynamics of the region's economic architecture.

In response to these developments, the project proposes to utilize the review mechanism of the AKFTA to expand its scope and ensure that it keeps pace with global trends and the new trade agendas being set by other international agreements. Recognizing the need to deepen ASEAN-Korea economic cooperation, this joint study focuses on emerging trade areas that are not yet covered by the AKFTA. The objective of this study is to provide a comprehensive analysis of recent global and regional trends, evaluate existing cooperation mechanisms between ASEAN and Korea, and identify potential areas for enhanced collaboration, particularly in forward-looking sectors. The proposed project will explore not only how to strengthen the economic linkages between ASEAN and Korea but also how to adapt trade rules and institutional frameworks to reflect new economic priorities.

To conduct the Study, the AKFTA-IC will hire consultants from ASEAN and ROK. The ASEAN Secretariat (ASEC) will be responsible for hiring one team of consultant (hereinafter “the consultant) for ASEAN while the Ministry of Trade, Industry, and Energy (MOTIE) will be responsible for hiring consultant for ROK.

Scope of work

The consultants will provide an overview of the AKFTA, identify emerging areas for cooperation, conduct a comparative analysis of global FTAs, present empirical or statistical evidence on the impact of ASEAN-Korea cooperation, and formulate recommendations for enhancing the FTA in emerging sectors. The joint report, prepared by the two consultants, will take into account the broader regional context and identify and address potential challenges, such as differing regulatory frameworks and infrastructure constraints.

Consultants’ qualifications

| Qualification | Weight |
| --- | --- |
| - The team of consultants – consisting of a Team Leader and researchers with relevant degrees and experience – should be experts in FTA related issues and new and emerging trade related issues and should demonstrate qualification in providing analytical, comparative study and technical assistance and capacity building solutions related to regional (multilateral and bilateral) FTAs. | 40% |
| - The consultants should have a few years of experience in working on FTA-related studies. Previous experience or consulting work with AKFTA Parties, international organizations and/or ASEC is preferable. The consultants should provide information on related projects and/or studies undertaken. | 20% |
| - The consultants should have demonstrated ability and experience in effectively facilitating group discussions and engaging positively and productively with various stakeholders, including government officials. The consultants should provide information on related projects and/or studies undertaken. | 10% |
| - The consultants should provide a comprehensive and detailed technical proposal consisting of: - Profile of the consulting firm (if applicable) or team of consultants providing information on the qualification and background of the consultants - Curriculum Vitae and profiles of each member of the team highlighting their relevant degrees and experience - Proposed approach and methodology for the Joint Study - Work plan - Approach to achieve the targets - Timelines for deliverables | 30% |

- Outputs

  - Detailed contents of the study are enumerated below:

- Executive Summary. This element of the Study will provide a summary of key findings and recommendations of the Study. A summary form of the Study may be released to the public upon the approval of the AKFTA IC.

- Literature Review. The study will gather insights from existing academic literature, policy reports, and international agreements related to ASEAN, Korea, and global trade to identify recent economic trends in the region and the policy priorities of ASEAN and Korea. Sources of literature can include academic journals on international trade and regional cooperation (e.g., Journal of International Economics, World Development), policy reports from ASEAN, Korean government, and global organizations (e.g., World Bank, IMF, OECD), as well as existing Free Trade Agreements (FTAs) and regional agreements between ASEAN and Korea.

- Comparative Study.The project will analyze the scope and provisions related to emerging areas by comparing global FTAs with the AKFTA.  By comparing FTAs, the project will identify best practices and lessons learned from other FTAs that can be applied to the AKFTA to enhance its effectiveness in promoting trade, investment, and economic development

- Best Practices Analysis. To identify effective strategies for enhancing cooperation in emerging areas, the project will analyze successful case studies from different FTAs. By examining common features and best practices across these agreements, the project can identify effective approaches for promoting cooperation in emerging areas such as green economy and supply chain resilience. This comparative analysis can provide valuable insights for policymakers and stakeholders seeking to strengthen regional integration and promote sustainable development through cooperation in emerging sectors.

- Impact analysis. The project will examine changes in economic outcomes, such as trade flows, investment patterns, to analyze the impact of ASEAN-Korea cooperation in emerging sectors. This analysis will help to identify the specific benefits and challenges associated with cooperation in these emerging areas.

- Recommendations. The project will formulate recommendations for enhancing the AKFTA in emerging sectors, including proposed structure and contents (commitments, institutional mechanism, etc.) of trade rules agreement between Korea and ASEAN. The joint report will take into account the broader regional context and identify and address potential challenges, such as differing regulatory frameworks and infrastructure constraints.

  - In conducting the joint study, the following activities will be carried out by the selected Consultants:

Activity 1: 	Submission of the Initial Draft Report

The initial draft report will cover all sections outlined in the agreed-upon structure. Also, the consultants shall adhere to the submission timeline and share the draft report with the counterpart consultant.

Activity 2:	Submission of the Final Report

The Final Report would incorporate comments, corrections, and recommendations from ASEAN Member States, Korea and the ASEAN Secretariat. Also, the consultants shall adhere to the submission timeline and collaborate in finalising the draft report with the counterpart consultant.

- Timeline and Deliverables

| Milestones | Activities | Timeline |
| --- | --- | --- |
| 1 | Submission of an initial draft report to AKFTA IC | May 2025 |
| 2 | Submission of comments to draft report and revisions | May – June 2025 |
| 3 | Submission of final report to the AKFTA IC through the ASEAN Secretariat | End of June 2025 |
| 4 | Approval of the final report by the AKFTA IC | July 2025 |
| 5 | Submission of final report to SEOM-ROK and AEM-ROK | August – September 2025 |
| 6 | Submission of project completion report and financial report | October 2025 |

- * In the event that the contract with the consultants is deferred from the scheduled timeline, the project timeline will be adjusted accordingly to reflect the length of the delay. However, despite any potential delays, it is essential that all parties (ASEAN, ROK, the Consultants) involved ensure the project is completed by 2025 to align with the agreed-upon objectives.

- Monitoring and Evaluation

- The consultants can confer with the ASEC’s External Economic Relations Division (EERD) or MOTIE for any questions or clarification on this project. The ASEC and MOTIE will provide the necessary documents and data as needed by the Consultations. The Consultants will work closely with ASEC and MOTIE to ensure that the timeframe described in the Indicative Work Plan are achieved.

- Submission of Proposals

- In conformance to the ASEAN Secretariat’s Financial Rules and Administrative Procedures (AFARP), the Consultant shall submit the applications in two separate documents: Technical Proposal and Financial proposal.

- Technical Proposal

- The technical component should contain the following information:

- A brief discussion indicating the prospective Consultant’s understanding of the project’s purpose;

- A discussion of how the prospective Consultant proposes to approach the project including but not limited to methodology to undertake the assignment;

- Brief discussion on the consultant’s or firm’s past experience in undertaking similar work and brief summary of projects undertaken (Please provide links to the publications if available, or enclose selected publications in soft-copy in the application);

- Names and curriculum vitae of associates, subcontractors, personnel or employees who will be engaged in the performance of services (if any);

- A sample of written work of similar nature as described in the output of this ToR that demonstrates suitability to carry out this project.

- Other information to substantiate the capacity of applicants to undertake the project.

- Financial Proposal

- Financial proposal should specify all costs (in USD) for undertaking the project including but not limited to:

- Professional services fee for completing all deliverables;

- Management and/or operational fees (if any), which include all costs incurred by the person for internal coordination, communication, travels and any other associated project management cost;

- Other costs that may be incurred in undertaking the project.

- Additional Notes on Terms and Conditions of the Project

  - Any future studies/reports/analysis in any form of intellectual property rights (including but not limited to patents, copyright and any related rights) submitted by the Contractor to ASEAN arising out of or in connection to the services performed by the Consultant to ASEAN shall belong to ASEC under the name of ASEAN only;

  - Successful bidder shall agree to be bound by and to sign the Special Services Agreement (SSA) with all requirements under the terms and conditions provided therein; and

  - As an intergovernmental organisation, ASEAN shall not be responsible for any tax(es), levy, tax claim or any tax liability which may be imposed by any law in relation to any amount payable by the ASEAN Secretariat.