TERMS OF REFERENCE (“TOR”)

FOR CONSULTANTS TO CONDUCT

THE JOINT STUDY ON DIGITAL TRADE

- Background

The 17th ASEAN Economic Ministers (AEM)-Republic of Korea (ROK) Consultations noted the importance of reviewing the ASEAN-Korea Free Trade Area (AKFTA) agreements with a view to ensuring its relevance to business and to maintaining the AKFTA as an important platform in expanding bilateral trade and investment between ASEAN and Korea. To this end, the AKFTA Implementing Committee (IC) agreed to conduct a Joint Review Study (JRS) of the AKFTA in 2022 as a reference for the possible upgrade of the AKFTA.

To complement the JRS, ROK undertook a self-funded ASEAN-Korea Digital Trade Research to analyse digital trade in ASEAN and ROK and provide recommendations on the appropriate digital trade cooperation framework between the two. The Digital Trade Research was undertaken by the Korea Institute for Industrial Economics and Trade (KIET). It was finalised and reported to the 20th AEM-ROK Consultation in August 2023, during which the Ministers tasked the AKFTA IC to discuss the next steps, including ways to foster closer digital cooperation between ASEAN and ROK.

The AKFTA currently does not have any digital trade provisions and given the exponential growth in the digital economy and e-commerce in recent years, the ASEAN-Korea Digital Trade Research and JRS recommended the addition of an independent Agreement on Digital Trade within the overall framework of the AKFTA.

The 20th AKFTA IC Meeting in March 2024 approved the final report of the JRS and agreed to undertake a further joint study on Digital Trade utilising the ASEAN-Korea Economic Cooperation (AKEC) Fund to serve as an additional reference to the JRS for the possible AKFTA upgrade.

To conduct the Study, the AKFTA-IC will hire consultants from ASEAN and ROK. The ASEAN Secretariat (ASEC) will be responsible for hiring one team of consultant (hereinafter “the consultant) for ASEAN while the Ministry of Trade, Industry, and Energy (MOTIE) will be responsible for hiring consultant for ROK.

Scope of work

The consultant will conduct a comprehensive study by: (a) taking into account the outcomes of the Korea-funded ASEAN-Korea Digital Trade Research; (b) reviewing the digital trade landscape, including challenges and opportunities, in each ASEAN Member States (AMS) and ROK; and (c) providing concrete recommendations on how to enhance digital trade rules and related cooperation between ASEAN and ROK under the AKFTA upgrade while taking into consideration the level of development and readiness of AKFTA Parties. Based on the outcomes of the study, ASEAN and ROK may discuss the way forward on digital trade in the possible upgrade of the AKFTA, including its potential parameters.

Consultants’ qualifications

| Qualification | Weight |
| --- | --- |
| - The team of consultants – consisting of a Team Leader and researchers with relevant degrees and experience – should be experts in FTA related issues and digital trade related issues and should demonstrate qualification in providing analytical, comparative study and technical assistance and capacity building solutions related to regional (multilateral and bilateral) FTAs. | 40% |
| - The consultants should have a few years of experience in working on FTA-related studies. Previous experience or consulting work with AKFTA Parties, international organizations and/or ASEC is preferable. The consultants should provide information on related projects and/or studies undertaken. | 20% |
| - The consultants should have demonstrated ability and experience in effectively facilitating group discussions and engaging positively and productively with various stakeholders, including government officials. The consultants should provide information on related projects and/or studies undertaken. | 10% |
| - The consultants should provide a comprehensive and detailed technical proposal consisting of: - Profile of the consulting firm (if applicable) or team of consultants providing information on the qualification and background of the consultants - Curriculum Vitae and profiles of each member of the team highlighting their relevant degrees and experience - Proposed approach and methodology for the Joint Study - Work plan - Approach to achieve the targets - Timelines for deliverables | 30% |

- Outputs

  - Detailed contents of the study are enumerated below:

- Executive Summary. This element of the Study will provide a summary of key findings and recommendations of the Study. A summary form of the Study may be released to the public upon the approval of the AKFTA IC.

- Impact analysis. Assess the impact of cross-border trade, including quantifying current volume of digital trade between AMS and ROK and its benefits in terms of trade to businesses and economies of ASEAN, individual AMS, and ROK.

- Gap analysis. Identify opportunities and challenges and assess gaps in the digital trade ecosystem between AMS and ROK, through taking stock of existing national policies, laws, regulations and initiatives relating to the digital trade and digital economy. Review the digital infrastructure, digital skills, digital divide and digital regulatory frameworks encountered by ASEAN and ROK businesses, traders, and investors.

- Comparative analysis. Review potential provisions and legally binding obligations related to digital trade in existing agreements to which ASEAN, ASEAN Member States, and ROK are collectively or individually parties or members of. Review provisions in related global initiatives and agreements such as the World Trade Organization’s Joint Statement Initiative on E-commerce, the Framework Agreement on Facilitation of Cross-border Paperless Trade in Asia and the Pacific (CPTA), the UNCITRAL Model Law on Electronic Commerce, the United Nations Convention on the Use of Electronic Communications in International Contracts, UNCITRAL Model Law on Electronic Transferable Records, and may take into consideration the important elements being discussed under the ASEAN’s Digital Economy Framework Agreement (DEFA), to identify what ASEAN and ROK could consider exploring

- Recommendations. Provide recommendations in the following:

  - For ASEAN and ROK at the individual and regional levels with the goal of fostering a conducive digital trade environment between ASEAN and ROK, which may include but will not be limited to identifying initiatives and pilot projects, suggestions on capacity building efforts and proposals for ASEAN and ROK to enhance human capital infrastructure (regulatory and technological);

  - On specific digital trade areas to be included, the mechanism (e.g., through a chapter in AKFTA or a separate standalone agreement) and exploring provisions that can be undertaken in the possible upgrade of the AKFTA, whilst taking into account the varying levels of development and digital trade policies in ASEAN and ROK; and

  - For potential capacity building activities to help AMS and ROK develop and improve capabilities and capacity to support the implementation of digital trade provisions.

  - In conducting the Study, the following activities will be carried out by the selected Consultants:

Activity 1: 	Submission of the Initial Draft Report

The initial draft report would cover all sections in the outline agreed, including the comparative study and gap analysis. It will also provide initial data sources, proposed interviews, consultations, questionnaires (if any) and timelines for the completion of the report.

Activity 2:	Submission of the Final Report

- The Final Report would incorporate comments, corrections, and recommendations from ASEAN Member States, Korea and the ASEAN Secretariat.

- Timeline and Deliverables

| Milestones | Activities | Timeline |
| --- | --- | --- |
| 1 | Submission of an initial draft report to AKFTA IC | May 2025 |
| 2 | Submission of input by AKFTA IC and revisions to the Initial Draft | May – June 2025 |
| 3 | Submission of final report to AKFTA IC | End June 2025 |
| 4 | Approval of final report by AKFTA IC | July 2025 |
| 5 | Submission of final report to SEOM-ROK and AEM-ROK | August – September 2025 |
| 6 | Submission of project completion report and financial report | October 2025 |

- * In the event where the contract with the consultants is deferred from the scheduled timeline, the project timeline will be adjusted accordingly to reflect the length of the delay. However, despite any potential delays, it is essential that all parties (ASEAN, ROK, the Consultants) involved ensure the project is completed by 2025 to align with the agreed-upon objectives.

- Monitoring and Evaluation

- The Consultants can confer with the ASEC’s External Economic Relations Division (EERD) or MOTIE for any questions or clarification on this project.  The ASEC and MOTIE will provide the necessary documents and data for as needed by the Consultations. The Consultants will work closely with ASEC and MOTIE to ensure that the timeframe described in the Indicative Work Plan are achieved.

- Submission of Proposals

- In conformance to the ASEAN Secretariat’s Financial Rules and Administrative Procedures (AFARP), the Consultant shall submit the applications in two separate documents: Technical Proposal and Financial proposal.

- Technical Proposal

- The technical component should contain the following information:

- A brief discussion indicating the prospective Consultant’s understanding of the project’s purpose;

- A discussion of how the prospective Consultant proposes to approach the project including but not limited to methodology to undertake the assignment and list of possible reference materials taking into account the targets to complete the project;

- A brief summary of the prospective Consultant’s expertise and knowledge in the application and implementation of Free Trade Agreements (FTAs) and digital trade, including the application of advisory work in disseminating benefits of FTAs to stakeholders;

- Brief discussion on the consultant’s or firm’s past experience in undertaking similar work and brief summary of projects undertaken (Please provide links to the publications if available, or enclose selected publications in soft-copy in the application);

- Names and curriculum vitae of associates, subcontractors, personnel or employees who will be engaged in the performance of services (if any);

- A sample of written work of similar nature as described in the output of this ToR that demonstrates suitability to carry out this project.

- Other information to substantiate the capacity of applicants to undertake the project.

- Financial Proposal

- Financial proposal should specify all costs (in USD) for undertaking the project including but not limited to:

- Professional services fee for completing all deliverables;

- Management and/or operational fees (if any), which include all costs incurred by the person for internal coordination, communication, travels and any other associated project management cost;

- Other costs that may be incurred in undertaking the project.

- Additional Notes on Terms and Conditions of the Project

  - Any future studies/reports/analysis in any form of intellectual property rights (including but not limited to patents, copyright and any related rights) submitted by the Contractor to ASEAN arising out of or in connection to the services performed by the Consultant to ASEAN shall belong to ASEC under the name of ASEAN only;

  - Successful bidder shall agree to be bound by and to sign the Special Services Agreement (SSA) with all requirements under the terms and conditions provided therein; and

  - As an intergovernmental organisation, ASEAN shall not be responsible for any tax(es), levy, tax claim or any tax liability which may be imposed by any law in relation to any amount payable by the ASEAN Secretariat.

*******

The scope of potential review areas includes but not limited to digital connectivity and digital infrastructure, paperless trading, digital payments, data governance, cyber security, digital talents, electronic transaction framework, electronic authentication and electronic signatures, electronic contracts, digital identifies, electronic invoice, standards and conformity assessment for digital trade, artificial intelligence and emerging technology, cooperation on competition policy, online consumer protection, and cross-border transfer of information by electronic means