TERMS OF REFERENCE

Consultant for the Evaluation of The ASEAN Magazine Project

- Background

The ASEAN magazine, a unique platform that provides in-depth analyses on issues affecting ASEAN, is known for its easy-to-understand manner and high editorial standards. It communicates programmes and achievements of the ASEAN Socio-Cultural Community (ASCC) pillar and the larger ASEAN Community to build a better understanding of the work among people in the region and beyond.

The magazine, which made its debut in May 2020 with the support of the ASEAN-India Fund, has been a resounding success and have garnered positive feedback from numerous readers and subscribers, earning high recognition within ASEAN.

The Phase 1 of the project ran from 2019-2021, and Phase 2, from 2021-2023. Currently, the project is in its third phase (2024-2026), supported by ASEAN-India Fund and is expected to be completed by March 2026. The third phase of the project aims to produce 16 regular and special issues. Regular issues comprise 56 pages and feature both a thematic and general section, covering important issues and ASEAN’s projects implemented to address these issues. Special issues are 40 pages long, focusing on one issue that needs highlighting in a timely fashion or prepared to support a high-level event.

Considering that the project has entered its third phase, the ASEAN Secretariat is looking for a Consultant to evaluate the different aspects of the implementation of The ASEAN magazine project. As part of the monitoring and evaluation measures for this long-running project, the project has included the hiring of an external evaluator among its activities. This is also in line with the Guidelines for the Implementation and Monitoring of the ASEAN Cooperation Projects which states that project with a duration of more than one year need to be evaluated.

- Objectives

The objective of this evaluation is to assess the outcomes and impact of The ASEAN Magazine Project from Phase 1 to Phase 3. This evaluation is crucial in determining whether the project was implemented effectively and reached its goals and targets, and recommending ways forward including areas for improvement, and sustainability of the project. Specifically, the evaluation aims to:

  - To evaluate the quality of the publication and its contribution/impact, specifically:

    - Whether it has increased public visibility of the work and benefits of ASEAN

    - Whether it has created a premier source of information, perspectives and analysis on ASEAN and ASCC issues, developments and interventions

    - Whether voices, viewpoints and stories of ASEAN citizens are well articulated in the magazine

  - To review the efficiency of the project’s management and processes; and

  - Following the review of the project’s effectiveness and impact as well as efficiency of its process, to provide recommendations regarding the sustainability of the project to adapt and respond to the evolving information needs of ASEAN.

- Scope of Evaluation

This evaluation seeks to answer key questions regarding effectiveness and quality of outputs of the project, relevance and outcomes, coherence and efficiency of project management and processes, and operations This section outlines the scope of the evaluation, detailing the specific questions that will guide the assessment and the boundaries within which the evaluation will be conducted.

- Effectiveness and quality of outputs or deliverables which include:

- progress towards or achievement of expected outputs from Phase 1 to 3

- range of topics covered

- diversity, expertise and credibility of authors or contributors

- presence of and adherence to editorial standards and ethical standards

- readability and clarity of content

- visual appeal

- distribution strategy and accessibility of the content in different formats and platforms

- Relevance, outcomes, and impact of the magazine which include:

- alignment with or contribution to ASEAN’s vision and community-building and strategic priorities as well as ASEAN’s/ASCC’s communication and outreach needs

- reach and circulation of the magazine’s print and digital versions

- audience engagement or interaction with magazine content or message (e.g., social media comments, shares, likes)

- contribution to knowledge generation/citation impact

- collaborations and partnerships formed

- changes in different user groups’ perception and understanding of, or attitude towards ASEAN

- Coherence and efficiency of project management and processes which include:

- coherence or synergy with ASEAN’s overall communication strategy and other communication initiatives

- clarity, efficiency, and timeliness of administrative procedures, production workflow, and delivery

- management and utilisation of resources: budget, time, staff

- oversight and reporting structure

- responsiveness to lessons learned from and feedback about previous project phases

- Sustainability

- relevance in its current format and medium

- existence of other financing options to continue or upscale the project

- strength of institutional commitment and support to continue or upscale the project

- structures and capacities in place to sustain the project

- Outputs and deliverables

The consultant is expected to submit the following deliverables:

- Evaluation plan that details how the evaluation will be conducted. It should specify the evaluation questions, data sources and collection methods, activities, and timeline

- Evaluation report that includes the findings, key takeaways/insights, and recommendations

- Evaluation Methodology

The evaluation consultant shall use the most relevant methodology to achieve the evaluation objectives. The ASCC Analysis Division will assist in providing the project information needed for the evaluation including all project documents and data, web and social media analytics, among others.

- Implementation Arrangements

The Consultant shall liaise closely with the ASCC Analysis Division, particularly in conducting interviews with key stakeholders.

The work will be conducted remotely, and in-person meetings, when needed, will be conducted in the ASEAN Secretariat/Headquarters in Jakarta.

The evaluation consultant shall maintain the privacy and confidentiality of all collected data and shall not disclose such data to any third party.  All data and resulting outputs are the intellectual property of ASEAN.

- Duration of Service

The Consultant is expected to submit the final evaluation report by August 2026 with the following indicative timeline:

| Activities | Indicative Timeline |
| --- | --- |
| Submission and review of Evaluation Plan | May 2025 |
| Data collection | June 2025 |
| Data analysis | July 2025 |
| Presentation of preliminary findings | 1st week of August 2025 |
| Submission and review of first draft of evaluation report | 3rd week of August 2025 |
| Submission of final version of evaluation report | 2nd week of September 2025 |

The timeline is subject to change upon discussion with the ASCC Analysis Division.

- Payment Schedule

The payment for this project will be released in three tranches as follows:

| No | Upon submission to the ASEAN Secretariat of the following work | Payment Schedule | Amount |
| --- | --- | --- | --- |
| 1 | Evaluation Plan | Upon approval of the ASEAN Secretariat of the submitted Evaluation Framework | 30 % |
| 2 | First draft of Evaluation Report | Upon approval of the ASEAN Secretariat of the submitted first draft of the evaluation report along with the data collection during the evaluation process (including transcripts of interviews and other data). | 40 % |
| 3 | Final evaluation Report | Upon approval of the ASEAN Secretariat of the submitted final evaluation report and presentation. | 30 % |

- Technical Requirements

The project requires a reputable consulting firm (or a joint venture/consortium/association), or Expert Consultant(s) with demonstrated expertise in development monitoring and evaluation.  The Consultant is expected to bring a strong understanding of impact evaluation and employ sound research methodologies for the evaluation. Interested bidders should demonstrate the following in the submitted technical proposal:

  - Provide institution/company profile that highlights the background of the company or a cover letter with summary of relevant experience for individual applicants that demonstrate:

- Ten (10) years of experience on evaluating projects, especially in the areas of media and communication or communication-related projects.

- Experience in providing general consultancy and advisory services within an ASEAN scope.

  - Provide verifiable and very good portfolio of previous evaluation work;

  - Provide a relevant client list with testimonials from four current or past clients that can be used for reference checking;

  - Provide very clear methodology and evaluation framework for the whole project which clearly outlines objectives and project approach, including but not limited to the methodology used for data collection;

  - Provide a copy of past evaluation reports (can be redacted for confidentiality).

  - Provide Curriculum Vitae (CV) for all personnel to be involved in the project that highlights the following criteria:

- Expertise in evaluating projects, especially in the areas of media and communication. Experience evaluating international programmes or projects is preferable.

- Strong management and implementation capabilities for delivering the required outputs.  The consultant should have demonstrated experience in managing complex monitoring and evaluation projects and facilitating multi-stakeholder processes. Please provide CVs of all proposed team member/s.

- Strong capacity for data collection, analysis, and report writing, with excellent communication skills, both oral and written.  The ability to communicate clearly and effectively to diverse audiences is essential.

- Knowledge of and previous experience in programme and project management, including monitoring and evaluation. Excellent command of written and spoken English, with proven ability to work harmoniously in a team environment with diverse groups of individuals in cross-cultural and international settings.

- Financial Requirement

A detailed financial proposal indicating the costs (IDR for local bidders and USD for international bidders) required for undertaking the assignment. The financial proposal should indicate a “lump sum amount” for the expected tasks specified in the terms of reference.

. . . . .