## Spec Form-For Invitations
For Invitations
SPECIFICATION FORM
Repalacement of Flooring Security Post Trunojoyo
Closing date for Quotation Submission: Refer to the invitation and web advertisement (asean.org)
No. | Items Description |  | Qty | UoM | Unit Price (IDR) | Total Price (IDR)
1 | Repalacement of Flooring Security Post Trunojoyo: - Replace existing floor with Wood Plastic Composite (WPC) Thickness 22-25mm, Hollow Series - Include dismantle and removing debris - Include accessories (joist connection, side cover, stainless clip, etc) - Include spare material 5% - Include installation of new floor foundation with existing floor height level (Pedestal concrete K-255, 8mm rebar) |  | 45 | m2 | Vendor to fill | Vendor to fill
General Requirements & Notes : 1) The contractor must provide material, supporting tools, equipment and manpower to complete the work 2) The contractor must comply with safety standards while working and maintain work without any accident or damage to ASEC property (provide safety net, personnel protective equipment, etc). If there is any damage occurs caused by the vendor work, the vendor must repair until satisfactory condition and approved by ASEC. 3) The contractor is required to ensure the working area remains tidy and clean 4) The contractor must have minimum 3 years experiences in construction works (proof must be submitted with quotation) 5) The contractor must submit sample material and data sheet along with quotation 6) The contractor must provide warranty letter before submitting final invoices 7) The contractor is strongly advised to attend the site visit to understand the nature of the work. Request for drawing and/or additional payment due to contractor's absent from the site visit will not be entertained. Working Time : weekdays : 05.30pm - 10.00pm weekend or national holiday : 08.00am - 10.00pm
Total | [5 empty] | 0
Delivery date |  | : After PO; works must be completed by end of July 2026
Availability of stock |  | : Ready Stock
Warranty (required) |  | : 10 year (warrnty letter must be submit before submitting invoice)
Terms of payment |  | : 10% Down Payment, 90% after all work has been completed
Validity of Quotation |  | : 90 days
General guideliens /Ketentuan:
1 | Please attach this Specifications Form to your quotation with your signature below or company's stamp;
Mohon melampirkan Spec. form ini pada penawaran disertai tanda tangan PIC atau stempel perusahaan;
By signing this Specification Form, you/your company agree to fulfil with all requirements as stated above.
Dengan menandatangani Form Spesifikasi ini, Anda/perusahaan Anda setuju untuk memenuhi semua kriteria tersebut diatas.
2 | Please state the availability of stocks for the above items;
Mohon cantumkan ketersediaan stock barang-barang diatas;
3 | All items provided shall be genuine. Shall the above items provided are not genuine, we will cancel the purchase of the above items;
Semua barang yang disediakan wajib barang asli. Apabila barang-barang di atas ditemukan tidak asli,
maka kami akan membatalkan Purchase Order yang sudah diterbitkan.
4 | The price in this quotation shall be valid for 90 (ninety) days commencing on the date of submission of quotation;
Harga satuan yang tertera pada penawaran wajib berlaku selama 90 (sembilan puluh) hari terhitung sejak tanggal penawaran;
5 | Vendor may use Faktur Pajak 040 to collect VAT by inserting this NPWP: 0224 6469 7605 3000
Vendor dapat menggunakan Faktur Pajak 040 untuk memungut PPn dengan NPWP berikut: 0224 6469 7605 3000
6 | The ASEAN Secretariat reserves the rights to take all or only selected goods/works/services.
ASEAN Secretariat berhak untuk mengambil semua atau hanya barang/pekerjaan/jasa tertentu.
[Signature or Company's Stamp]
[Vendor to fill in]
…………………………………..
Contact Person:
Company:
Date/Tanggal:

## Sheet1
| Electricity Consumption CHILLER 1 | [5 empty] | Electricity Consumption CHILLER 2
Date | 8:00 | 10:00 | 14:00 | Average |  | Date | 8:00 | 10:00 | 14:00 | Average
2026-03-02 | 120.8 | 146.6 | 144.4 | 137.2667 |  | 2026-03-02 | 92 | 111.7 | 110.4 | 104.7
| 108.9 | 112.2 | 141.2 | 120.7667 |  |  | 84.1 | 86.2 | 107.4 | 92.5667
| 111.1 | 120.3 | 130.5 | 120.6333 |  |  | 111.1 | 120.3 | 130.5 | 120.6333
| 123.9 | 148.1 | 153 | 141.6667 |  |  | 123.9 | 148.1 | 153 | 141.6667
| 114.9 | 109.5 | 111.7 | 112.0333 |  |  | 114.9 | 109.5 | 111.7 | 112.0333
|  |  |  | #DIV/0! | 126.4733 |  |  |  |  | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!
|  |  |  | #DIV/0! | [5 empty] | #DIV/0!