TERMS OF REFERENCE

International Expert on Statistics of International Trade in Services (SITS)

Project Name:

Enhancing ASEAN Statistics of International Trade in Services (SITS) for Policy and Regional Integration Monitoring

Duration:

This consultancy will be undertaken on a part-time and remote basis for a period of up to eight (8) months, tentatively from August 2026 to March 2027. The final duration, commencement date, and work schedule are contingent upon the conclusion of the procurement process and may be modified subject to programme requirements and expert availability.

Background:

The services sector has emerged as a major contributor to ASEAN’s economic performance and integration, reflected in the sustained increase in services trade. To effectively monitor this development and support evidence-based policymaking, high-quality and timely Statistics of International Trade in Services (SITS) are important.  The ASEAN Community Statistical System (ACSS), through the Working Group on Statistics on International Trade in Services (WGSITS), plays an important role in improving the availability, quality and use of SITS to support ASEAN integration commitments and policy design. One of the key dimensions of quality in SITS is alignment with international standards and harmonisation of compilation practices among ASEAN Member States (AMS) to ensure comparability across countries and over time. Additionally, another critical need is the availability of more detailed partner-country breakdowns, which is currently varied among AMS, yet is crucial for monitoring the implementation and impacts of free trade agreements and other regional commitments.

The compilation of SITS in ASEAN is guided by international standards such as the UN Manual on Statistics of International Trade in Services and the IMF’s Balance of Payments and International Investment Position Manual. With the release of updated international manuals and the growing complexity of cross-border services, including digital trade in services, there is a need for AMS to assess current national methodologies, identify gaps and prepare a coordinated roadmap for improvement, and learn from HKSAR experience on their SITS compilation to build technical capacity of AMS for compiling and analysing SITS data that are aligned with international standards.

Objective

The objective of this project is to strengthen the quality and harmonisation of SITS in ASEAN through a coordinated regional approach. This will support improved regional comparability, monitoring of trade agreements, and informed economic policymaking.

Specifically, the project aims to:

- Assess national compilation practices against international standards;

- Identify methodological and institutional gaps;

- Develop a regional roadmap for harmonised implementation; and

- Enhance the capacity of AMS to compile and analyse SITS, including digital trade in services and detailed partner-country data.

Tasks/Responsibilities

In coordination with the WGSITS and ASEANstats, the International Expert shall undertake the following tasks:

- Inception and Work Planning

- Review relevant project documents and background materials.

- Develop the methodology, assessment framework, work plan, and timeline for the assignment.

- Design the questionnaire to compile information on current SITS compilation practices in AMS.

- Prepare and submit an Inception Report for ASEANstats' review and approval.

- Conduct a Regional Gap Analysis

- Review existing national compilation frameworks, methodologies, data sources, institutional arrangements, and dissemination practices of SITS in AMS.

- Assess the degree of alignment with international statistical standards, including the latest edition of the Manual on Statistics of International Trade in Services and the Balance of Payments and International Investment Position Manual.

- Identify methodology, coverage, classification and data gaps, including treatment of digital trade in services and availability of partner-country breakdowns.

- Conduct consultations with AMS and relevant stakeholders, as appropriate, to validate findings and gather information on national compilation practices and priorities.

- Develop a Regional Roadmap for Harmonised SITS Compilation

- Propose practical and sequenced actions to improve methodological alignment and harmonisation across AMS.

- Develop recommendations to enhance partner-country data compilation and reporting.

- Prepare a regional roadmap outlining short-, medium-, and long-term measures, including capacity-building priorities and coordination mechanisms.

- Conduct consultation and capacity-building workshop

- Prepare technical guidance materials on priority issues identified in the gap analysis.

- Facilitate and support technical workshops (in-person), including sharing relevant international and regional experiences in compiling trade in services statistics, including compilation of SITS by trade partner and alignment with the new standards, and facilitate the knowledge sharing session in collaboration with experts from HKSAR Census and Statistics Department.

- Provide advisory inputs to AMS on strengthening national compilation systems and metadata documentation.

- Reporting and Coordination

- Submit periodic progress updates to ASEANstats.

- Present key findings and recommendations to WGSITS and ASEANstats.

- Incorporate feedback from AMS and ASEANstats into final outputs.

- Contribute to the preparation of the final project report upon completion of all activities.

Expected Outputs

The International Expert is expected to deliver, but is not limited to, the following outputs within the 8-month consultancy period:

| Deliverable | Indicative Timeline* | Expected Output |
| --- | --- | --- |
| Milestone 1. Inception Phase |  |  |
| Inception Report | August 2026 | Inception Report detailing methodology, assessment framework, work plan, timeline, stakeholder consultation approach, and proposed structure of key outputs. |
| Milestone 2. Assessment and Roadmap Development Phase |  |  |
| - Draft Gap Analysis Report | September-October 2026 | Draft Gap Analysis Report assessing SITS compilation practices across AMS, including methodological alignment, data sources, institutional arrangements, digital trade in services, partner-country data, and priority gaps. |
| - Draft Regional Roadmap | October – November 2026 | Draft Regional Roadmap outlining strategic objectives, recommended actions, capacity-building priorities, implementation arrangements, and monitoring framework for harmonised SITS compilation. |
| Milestone 3. Consultation and Capacity-Building Phase |  |  |
| - Regional Consultation and Capacity-Building Workshop | November or December 2026 | Workshop conducted to validate findings, discuss methodological issues, strengthen AMS capacity, and facilitate knowledge sharing on SITS compilation and implementation of updated international standards. |
| - Workshop Report | Within 2-4 weeks after workshop | Workshop Report summarising discussions, feedback, recommendations, technical clarifications, and identified capacity-building needs. |
| - Activity Summary Report | December 2026 | Activity Summary Report outlining the activity conducted, observations on participants’ technical capacity and engagement, assessment of achievement of the intended objectives, key implementation challenges, and recommendations for future improvement. |
| Milestone 4. Finalisation Phase |  |  |
| - Final Gap Analysis Report | January – February 2027 | Final Gap Analysis Report incorporating comments and recommendations from AMS, WGSITS, and ASEANstats. |
| - Final Regional Roadmap | January – February 2027 | Final Regional Roadmap incorporating stakeholder feedback and providing an agreed framework for regional implementation. |
| - Contribute to project completion Report | March 2027 | Brief report summarising activities undertaken, key findings, recommendations, and proposed follow-up actions. |

*Indicative only and subject to adjustment based on the final project schedule.

Qualifications

The consultancy may be undertaken by either an individual consultant or a consulting institution. In the case of an institutional application, the proposed Team Leader shall meet the qualifications specified below, while the proposed team should collectively possess the required expertise and experience.

The consultant should meet the following minimum qualifications:

- Advanced degree (Master’s or PhD) in statistics, economics, econometrics, or a related discipline.

- Strong knowledge of international statistical standards, particularly the Balance of Payments and International Investment Position Manual and the Manual on Statistics of International Trade in Services.

- Demonstrable portfolio of working on statistics projects in particular in the field of SITS.

- Excellent analytical, drafting, and communication skills in English.

- Demonstrate professional experience and knowledge in facilitation, writing, and capacity building, including delivery of training/workshop.

Relevant Experiences

- At least ten (10) years of professional experience in macroeconomic statistics, Statistics of International Trade in Services (SITS), Balance of Payments (BOP) statistics, or related statistical fields.

- Demonstrated experience in compiling, analysing, or disseminating SITS and/or Balance of Payments statistics.

- Proven track record in undertaking statistical assessments, methodological reviews, gap analyses, development of roadmaps or action plans, and capacity-building activities related to official statistics.

- Demonstrable portfolio of projects related to SITS, trade in services statistics, Balance of Payments statistics, or related macroeconomic statistics at national, regional, or international levels.

- Experience working with national statistical offices, central banks, international organisations, or regional statistical cooperation initiatives is desirable.

- Previous experience supporting ASEAN statistical initiatives, particularly those related to SITS, will be considered an advantage.

Documents to be submitted

The proposal shall include the following documents demonstrating that the applicant meets the qualification and experience requirements specified in this Terms of Reference:

- Curriculum Vitae (CV) of the consultant (or Team Leader, in the case of an institutional application);

- Copies of academic degree certificates and relevant professional certifications, where applicable;

- A list of relevant assignments demonstrating experience in SITS, Balance of Payments, or related macroeconomic statistics, including the client, period of engagement, and scope of work; and

- Any other documentary evidence demonstrating compliance with the qualification and experience requirements specified in this Terms of Reference.

Consultancy Fee

The selected consultant shall be engaged under a lump-sum contract covering all services, outputs, and responsibilities required under the assignment. Travel-related expenses, where travel is approved and required under the project, including economy-class air tickets and Daily Subsistence Allowance (DSA), will be covered separately in accordance with ASEAN Secretariat policies and will not be included in the lump-sum consultancy fee. Other indirect costs including communication/coordination, logistics/office supplies, and desk research, will be borne by the Consultant as part of the contract.

Payments shall be made in instalments based on the satisfactory completion and acceptance of agreed deliverables and milestones, in accordance with the payment schedule as follows:

| Deliverable | Payment |
| --- | --- |
| Submission and acceptance of Inception Report | 20% |
| Submission and acceptance of Draft Gap Analysis Report and Draft Regional Roadmap | 30% |
| Completion of consultation/capacity-building workshop and submission and acceptance of workshop report and activity summary report. | 30% |
| Submission and acceptance of Final Gap Analysis Report, Final Regional Roadmap, and all final deliverables | 20% |

*****